## Slide 1
WORKFLOW
A week with this tool
research-pm
1 / 6
This is a markdown-based project manager that Claude operates. You do the work; Claude handles the planning, logging, and follow-ups. The small tags below are the commands Claude runs — a standup (today's plan), a digest (what shipped), a retrospective (what slipped).
MON
TUE
WED
THU
FRI
/week-plan
Methods — intro
2h · TNF
Admin + email
30m
MCF-7 passage
45m
Methods draft
2h · TNF
Dose-response
2h · TNF
1:1 Ravi
30m
1:1 prep (Sara)
25m
Results draft
2.5h · TNF
Organoid media
3h · Org
Lab meeting
1h
Notes + log
20m
Methods revise
2h · TNF
Assay prep
1.5h · Org
1:1 Sara
30m
Reagent order
15m
Intro polish
2h · TNF
MCF-7 passage
45m
/digest + /retro
30m
Plan next week
20m
CLAUDE RUNS
MONDAY
/week-plan
Drafts your top-5 for the
week. You edit.
MORNING
/standup
Today's 3 tasks, anything
overdue, calendar shape.
MORNING
/standup
Flags anything that slipped
from the day before.
MORNING
/standup
Drafts the 1:1 agenda for
your afternoon meeting.
FRIDAY
/digest + /retro
Summary of what shipped,
notes on what slipped.
Deep
Lab
Light
Meeting / ritual

## Slide 2
DAILY TOUCHPOINT
What you see each morning
research-pm
2 / 6
Two surfaces you'd open first thing: the dashboard (in a browser) and the standup (in Claude chat). Mockups below. Tell us what's missing or extra.
research-pm.github.io/dashboard
research-pm — Tuesday, Apr 21
ACTIVE PROJECTS
3 / 3
at WIP cap
WRITING STREAK
12 days
block held
OVERDUE
1
from Monday
ACTIVE PROJECTS
TNF paper
last · methods draft (2h) · next · figures v3
Organoid model
last · media v2 protocol · next · cell type B stable
R01 renewal
last · Aim 3 outline · next · preliminary data
QUARTERLY GOALS
TNF paper · Q2 draft (OKR)
67%
Organoid · Q2 baseline (narr.)
40%
Claude · morning standup
9:02 am
Good morning — standup for Tuesday, Apr 21.
TODAY'S 3
09:00–11:00
Methods revise
TNF paper › Methods drafted › Q2 draft complete
14:00–16:00
Media protocol v2
Organoid › Media v2 › Q2 baseline
16:15–17:00
1:1 with Sara
People › Sara owes 2 › 4-week cadence
OVERDUE
Figure 4 v1 (TNF) — due Monday. Re-slot, or push?
CALENDAR SHAPE
3h Deep morning · 2h Lab afternoon · 1 meeting
HEADS UP
Writing block skipped twice this week. Organoid log silent 4 days.

## Slide 3
GOAL STRUCTURE
How goals connect
research-pm
3 / 6
Year goals break into quarters, then projects, then weeks, then days. Quarterly goals come in two styles: OKR (Objective + measurable Key Results) for tight-clock work; narrative (status + paragraph) for exploratory work.
YEAR
QUARTER
PROJECT
WEEK
TODAY
YEAR GOAL · OKR
Publish TNF paper (Cell Reports, Oct 2026)
YEAR GOAL · NARRATIVE
Establish organoid model — 2 cell types, protocol
Q2 — Draft complete (OKR)
Key Result 1 — Methods drafted
100%
Key Result 2 — Figures v3
67%
Key Result 3 — Co-author review
0%
Q2 — Baseline working (narrative)
Media reliably reproducible. 2nd cell type has recurring contamination — root cause traced to shared incubator. Next: isolate. Status: on track.
CHECKPOINTS · each has a Definition of Done
Methods drafted
Results drafted
Figures v3
CHECKPOINTS · each has a Definition of Done
Media protocol v2
Cell type B stable
Doubling time char.
WEEKLY TOP-5 · max 1–2 per project
1 · Methods revise (TNF)
2 · Figure 4 v1 (TNF)
3 · Media protocol v2 (Organoid)
4 · 1:1 Sara (postdoc)
5 · R01 Aim 3 data outline
TODAY'S 3 · slotted into calendar blocks
09:00–11:00 Methods revise
14:00–16:00 Media protocol
16:15–17:00 1:1 Sara

## Slide 4
VISUALISE
One data source, two views
research-pm
4 / 6
All views come from the same markdown files. The Gantt (top) shows a project across months. The Plan Board (bottom) shows this week's calendar blocks. Move something in one view, the other updates.
PROJECT GANTT · TNF paper
APR
MAY
JUN
Writing
Intro
Methods
Results
Figures v3
Lab
Dose-response
Replicate
Collab
Co-author review
PLAN BOARD · week of Apr 20
MON 20
TUE 21
WED 22
THU 23
FRI 24
09
11
13
15
17
Methods
Admin
Methods
Dose-resp
Ravi
Results
Media
Lab mtg
Revise
Assay
Sara
Polish
Passage
/digest
same markdown

## Slide 5
MODIFY
Moving things around
research-pm
5 / 6
Drag the bar on the Gantt, or tell Claude in chat. Either way, every downstream block shifts — and you see the impact before anything saves. ("Cascade" = the knock-on effect.)
BEFORE
APR
MAY
JUN
Writing
Methods
Writing
Results
Writing
Figures v3
Collab
AFTER
APR
MAY
JUN
Writing
Methods
Writing
Results
Writing
Figures v3
Collab
DRAG
Grab the Methods bar, drop it a week later on the Gantt or Plan Board.
OR
SAY
“slip TNF methods by a week” in Claude chat.
IMPACT
Q2 Objective
→
on track → watch
Year goal
on track
Buffer on Figures v3
2 days remaining
Compress downstream
Tighten the next blocks to hit original date.
Accept the slip
Push Figures v3 deadline; Co-author review stays.
Cut scope
Drop 1 figure; stay on original timeline.

## Slide 6
OUTPUTS
Four things the tool produces
research-pm
6 / 6
A project page, a 1:1 agenda draft, a weekly report for a collaborator, and a time-estimate prompt. All come from the same markdown files. Mockups below.
ARTIFACT · PROJECTS/TNF-PAPER.MD
Project page — TNF paper
status: active
goal_model: okr
deadline: 2026-10-31 (Cell Reports)
collaborators: Prof Smith, Ravi (postdoc)
## Checkpoints
Methods drafted
Apr 15
DoD: 2000 words, cites done
Results drafted
May 15
DoD: numbers + structure
Figures v3
May 31
DoD: 6 of 6 finalised
Co-author review
Jun 15
DoD: all replies incorporated
ARTIFACT · /ONE-ON-ONE SARA
1:1 agenda draft — Sara (postdoc) · Apr 24
She owes me (2)
• Organoid protocol v2
committed Apr 8 · due Apr 22
• Figure 4 first draft
committed Apr 14 · due Apr 30
I owe her (1)
• Feedback on cell type B results
due Apr 23
Recent progress
• Media v2 reliable across 6 passages
• Cell type B contamination — root cause traced to incubator
Open blockers
• Antibody reorder pending — ETA Apr 28
ARTIFACT · /REPORT TNF FOR PROF-SMITH
Weekly report — TNF paper · for Prof Smith
Week of Apr 14 — Apr 20
Progress this week
✓ Methods section drafted (2000 words)
✓ Figures 1–3 finalised at v3
✓ Replicate run matches primary data within 5%
Next week
→ Results section drafting (target: Fri)
→ Figures 4–6 first pass
Your input needed
• Methods section comments before Results starts?
• Cell Reports 6-panel figure limit — stick to it?
Saved to exports/ · .md · .email.md · .slides.md
PROMPT · DURATION LEARNING
How long does this take? (learned from history)
Claude
Based on your last 8 figure drafts (median 2h 20m), I’ll block 2.5h tomorrow 09:00–11:30 in your protected writing block.
Confirm, or give a different length.
yes — confirm
Underlying data · meta/task-history.json
figure_draft: { median_min: 140, p90_min: 210, n: 8 }